SDC/ WASH Project Update

| Original | Activity | Original target | Changed to |  | Situation | Remark |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1.1 – A | Construction WASH Facilities (A): Installing water pipeline system and storage tanks for an IDPs camp in Daw Hso Ku, in Eastern Demoso | Demoso | Shadaw | 1 | Completed |  |
| 1.1.1 – B | Installing water pipeline system and storage tanks for an IDPs camps in Makrawshay village tract, Hpruso | Hpruso | Hpruso | 1 | Completed |  |
| 1.1.1 – C | Building a spring water catchment/pond in Hso Tel, Hpruso | Hpruso | Hpruso | 1 | Ongoing/ Completed by June | Changed to Kay Phoe Du School |
| 1.1.1 - D | Building a spring water catchment in Hsin Saka, Loikaw | Loikaw | Hpruso | 1 | Completed | Changed to Kaw Ta Kaw, Hoya |
| 1.1.1 – E | Building bio-filtration system in Hso Ta Shar, Hpruso and Demoso | Hpruso, Demoso, Loikaw and Shadaw | 2-Hso Ta Shar, 1-Hpruso, 1-Shadaw | 4 | Completed |  |

| Additional NEQ | Activity | Target Location | Changed to |  | Situation | Remark |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1.1 Add-A | Renovating water storage pond and installing filtration system in Loikaw | E Loikaw | Western Demoso | 1 | Ongoing/ completed by June | Changed to Larleh village |
| 1.1.1 Add-B | Installation of water pipelines + storage pond Hpruso | Hpruso | Hpruso | 1 | Completed | Ki Loh Pra, Hpruso |
| 1.1.1 Add-C | 2 Bio filtration system, Loikaw | East Loikaw | 1 Hue Pu Long, 1 Mayyu | 2 | 1 left to install |  |
| 1.1.1 Add-D | Distributing water storage tanks | Demoso, Hpruso | Demoso, Hpruso | 20 | 14 purchased and distributed | 6 remains |
| 1.1.1 Add-E | Rice bank | Huai Pu Long, Sho Ta Shar | Huai Pu Long | 1 | 50% completed | Completed by May |

Note: 2 Multiplier trainings remain (1 in Western in Demoso, 1 in Huai Pu Long)